Basic Scheduling

|  |  |  |
| --- | --- | --- |
| Tasks | Duration (Days) | Predecedors |
| A | 3 | - |
| B | 4 | A |
| C | 2 | A |
| D | 5 | B |
| E | 1 | C |
| F | 2 | C |
| G | 4 | D, E |
| H | 3 | F, G |

|  |
| --- |
|  |
| When is the delivery date? |
| It depends on the number of members work on this project in case two members only Project can be delivered after 19 days |
| Which tasks could be delayed without delaying the schedule? |

In this case tasks could be delayed without delaying the schedule: Tasks (C, E & F) I think it can delay 4 days only