## Slide 1
Tasks | Duration (Days) | Predecedors
A | 3 | -
B | 4 | A
C | 2 | A
D | 5 | B
E | 1 | C
F | 2 | C
G | 4 | D, E
H | 3 | F, G
Scheduling via PDM

## Slide 2
3 | 4 | 7
Task B |  | 
3 | 0 | 7
0 | 3 | 3
Task A |  | 
0 | 0 | 3
3 | 2 | 5
Task C |  | 
9 | 6 | 11
7 | 5 | 12
Task D |  | 
7 | 0 | 12
12 | 4 | 16
Task G |  | 
12 | 0 | 16
16 | 3 | 19
Task H |  | 
16 | 0 | 19
5 | 1 | 6
Task E |  | 
11 | 6 | 12
5 | 2 | 7
Task F |  | 
14 | 9 | 16
4
2
1
2
5
4
4
3
3

## Slide 3
When is the delivery date?
It depends on the number of members work on this project in case two members only Project can be delivered after 19 days
Which tasks could be delayed without delaying the schedule?
In this case tasks could be delayed without delaying the schedule: Tasks (C, E & F)